## Project planning
Project planning
Start of project |  | 2008-01-01
Number of days per time unit |  | 7
Data
Activities |  | Time | Preced. 1 | Preced. 2 | Preced. 3 | Preced. 4
A | A description | 2
B | A description | 3
C | A description | 2 | A
D | A description | 4 | A | B
E | A description | 4 | A | B | C | D
F | A description | 3 | C
G | A description | 5 | D | E
H | A description | 2 | F | G
I | A description
J | A description
K | A description
L | A description
M | A description
N | A description
O | A description
Result | [7 empty] | Diagram
Activities |  | ES | EC | LS | LC | Slack | Critical |  | Early start | Time usage | Start date | End date
A | A description | 0 | 2 | 1 | 3 | 1 | NO | A | 0 | 2 | 2008-01-01 | 2008-01-15
B | A description | 0 | 3 | 0 | 3 | 0 | YES | B | 0 | 3 | 2008-01-01 | 2008-01-22
C | A description | 2 | 4 | 5 | 7 | 3 | NO | C | 2 | 2 | 2008-01-15 | 2008-01-29
D | A description | 3 | 7 | 3 | 7 | 0 | YES | D | 3 | 4 | 2008-01-22 | 2008-02-19
E | A description | 7 | 11 | 7 | 11 | 0 | YES | E | 7 | 4 | 2008-02-19 | 2008-03-18
F | A description | 4 | 7 | 13 | 16 | 9 | NO | F | 4 | 3 | 2008-01-29 | 2008-02-19
G | A description | 11 | 16 | 11 | 16 | 0 | YES | G | 11 | 5 | 2008-03-18 | 2008-04-22
H | A description | 16 | 18 | 16 | 18 | 0 | YES | H | 16 | 2 | 2008-04-22 | 2008-05-06
I | A description | 0 | 0 | 18 | 18 | 18 | NO | I | 0 | 0 | 2008-01-01 | 2008-01-01
J | A description | 0 | 0 | 18 | 18 | 18 | NO | J | 0 | 0 | 2008-01-01 | 2008-01-01
K | A description | 0 | 0 | 18 | 18 | 18 | NO | K | 0 | 0 | 2008-01-01 | 2008-01-01
L | A description | 0 | 0 | 18 | 18 | 18 | NO | L | 0 | 0 | 2008-01-01 | 2008-01-01
M | A description | 0 | 0 | 18 | 18 | 18 | NO | M | 0 | 0 | 2008-01-01 | 2008-01-01
N | A description | 0 | 0 | 18 | 18 | 18 | NO | N | 0 | 0 | 2008-01-01 | 2008-01-01
O | A description | 0 | 0 | 18 | 18 | 18 | NO | O | 0 | 0 | 2008-01-01 | 2008-01-01
Project time: |  |  | 18
ES | Early start, enter when the activity earliest can start
EC | Early completion, enter when the activity at the earliest can be completed
LS | Late Start, enter when the activity at last can start without jeopardizing the entire project
LC | Late completion, enter how late the activity can be completed without putting the project in jeopardy
Slack is the time that an activity can be delayed without putting the project in jeopardy
Critical indicate if the activity must be carried out on scheduled time or not to allow the project to keep the deadline
Formulas:
End date = [Start date]+([Time usage]*'Project planning'!$C4)

## Calculations
Calculation of early start (ES)
Activities | Preced. 1 | Preced. 2 | Preced. 3 | Preced. 4
A | 0 | 0 | 0 | 0
B | 0 | 0 | 0 | 0
C | 2 | 0 | 0 | 0
D | 2 | 3 | 0 | 0
E | 2 | 3 | 4 | 7
F | 4 | 0 | 0 | 0
G | 7 | 11 | 0 | 0
H | 7 | 16 | 0 | 0
I | 0 | 0 | 0 | 0
J | 0 | 0 | 0 | 0
K | 0 | 0 | 0 | 0
L | 0 | 0 | 0 | 0
M | 0 | 0 | 0 | 0
N | 0 | 0 | 0 | 0
O | 0 | 0 | 0 | 0
Calculation of late completion (SF)
| A | B | C | D | E | F | G | H | I | J | K | L | M | N | O
A | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
B | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
C | 5 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
D | 3 | 3 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
E | 7 | 7 | 7 | 7 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
F | 18 | 18 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G | 18 | 18 | 18 | 11 | 11 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
H | 18 | 18 | 18 | 18 | 18 | 16 | 16 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
I | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
J | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
K | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
L | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
M | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
N | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
O | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
Minimum: | 3 | 3 | 7 | 7 | 11 | 16 | 16 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18